# Project brief

A practical starting point for a clear, manageable project.

Sample content is included. Replace bracketed prompts and example entries before use.

| Project | Planning details |
| --- | --- |
| [Project name] | Sample: Community resource library |
| Project lead / sponsor | [Role] / [Approving role] |
| Timing / budget | Sample: 6 weeks / 4,800 currency units |

# The outcome

Create a searchable library that helps the team find the right resource without asking around. The first release covers the 40 most-used documents.

# Why this matters

Resources currently live in several folders. People lose time looking for the latest version, and new team members do not know where to begin.

# What is included

| In scope | Out of scope |
| --- | --- |
| Content inventory and owner list | Replacing the organization’s document platform |
| One consistent naming system | Migrating every historic archive |
| Pilot with five users and a short guide | Custom mobile application |

# What success looks like

Sample acceptance targets: all 40 resources have an owner; five pilot users can find three assigned items; no broken links remain at handover.

# Delivery & decisions

Keep this page current as scope, dates or decisions change.

| Milestone | Owner | Due | Evidence |
| --- | --- | --- | --- |
| Inventory complete | Content lead | Week 1 | Approved inventory |
| Structure agreed | Project lead | Week 2 | Folder map |
| Pilot finished | Test lead | Week 4 | Feedback log |
| Handover | Sponsor | Week 6 | Acceptance checklist |

# Risks & dependencies

| Risk or dependency | Response / owner |
| --- | --- |
| Some documents have no owner | Assign an interim owner before migration. / Sponsor |
| Pilot volunteers have limited time | Book a 20-minute session in advance. / Test lead |
| Access permissions must be reviewed | Confirm access before release. / System owner |

# Open decisions

| Decision needed | Decision owner | By when |
| --- | --- | --- |
| Choose the location for the library | Sponsor | End of Week 1 |
| Confirm which 40 documents come first | Content lead | End of Week 1 |

# Approval & handover

Approved by: [role]   Date: [date]   Version: [version]

Handover location: [link or folder]

Before sharing: replace examples, confirm owners, agree on success measures, and remove sections that do not apply.